## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
D-001 | Team B | 2025-12-05 | Model not detecting images properly | Sprint 2 | Team B | Functional | Adjusted image preprocessing | 2025-12-06 | Closed | Verified
D-002 | Team B | 2025-12-17 | ICD-10 code generation failed for certain cases | Sprint 3 | Team B | Logical | Updated disease-code mapping | 2025-12-18 | Closed | Validated
D-003 | Team B | 2025-12-30 | Output visualization not displaying results | Sprint 4 | Team B | UI | Fixed frontend rendering script | 2025-12-31 | Closed | Stable Team

## Sheet2
Logical
User Interface
Maintainability
Standards
Others